## Risk Table
Risks | Type | Probability | Impact | RIS
Time management | Experienced staff | 0.3 | 6 | RIS1
Payment method not clear | Non-serious customer | 0.6 | 7 | RIS2
API is not easily accessible | Development issue | 0.7 | 6 | RIS3
Untrained staff | Development issue | 0.9 | 9 | RIS4
Privileges Ambiguity | Development issue | 0.8 | 9 | RIS5
Stakeholders Ambiguity | Development issue | 0.7 | 7 | RIS6
Threshold Level | Probability | 0.6
| Impact | 7

## RIS1
ID | Date | Probabilty | Impact | Description | Refinemnet | Mitigation / Avoidance | Contingency Plan | Status | Assigned
RIS1 | 2022-04-12 | 0.3 | 6 | Time management | Subcondition 1: | 1: Make requiremnrts clear ASAP | 1: Keep in conatct wiith client | Monitoring | Project Manager
[5 empty] | Not clear requirements | 2: Keep good relation with staff
[5 empty] | Subcondition 2: | 3: Encourage staff's effort
Poor management

## RIS2
ID | Date | Probabilty | Impact | Description | Refinemnet | Mitigation / Avoidance | Contingency Plan | Status | Assigned
RIS2` | 2022-04-12 | 0.6 | 7 | Payment method not clear | Subcondition 1: | 1: Clear requirements ASAP | 1: Schedule meeting with client | Monitoring | Project Manager
Requirements are not clear

## RIS3
ID | Date | Probabilty | Impact | Description | Refinemnet | Mitigation / Avoidance | Contingency Plan | Status | Assigned
RIS3 | 2022-04-12 | 0.7 | 6 | API is not easily accessible | Subcondition 1: | Look for alternative solution if possible | 1: Look for the efficient API | Monitoring | Project Manager
[5 empty] | API is paid |  | 2: Discuss it with the client
Subcondition 2:
API is not that efficient

## RIS4
ID | Date | Probabilty | Impact | Description | Refinemnet | Mitigation / Avoidance | Contingency Plan | Status | Assigned
RIS4 | 13/12/2022 | 0.9 | 9 | Untrained Staff | Subcondition 1: | 1: Training workshop | 1: Keep motivation alive in team | Monitoring | Project Manager
[5 empty] | Low competency | 2: Reward system
3: Encourage staff's effort

## RIS5
ID | Date | Probabilty | Impact | Description | Refinemnet | Mitigation / Avoidance | Contingency Plan | Status | Assigned
RIS5 | 13/12/2022 | 0.8 | 9 | Privileges Ambiguity | Subcondition 1: | 1: Meeting at third place | 1: Keep customer aware of risk of wastage of source | Monitoring | Project Manager
[5 empty] | Requirements are not clear | 2: Keep customer aware of risk
[5 empty] | Subcondition 2: | 3: Show different possibities
Customer is not clear about the system

## Details
Components | Drivers | Scale
Performance | Marginal | 3
Support | Marginal | 3
Cost | Critical | 8
Schedule | Catastrophic | 10
Risk | Performence | Support | Cost | Schedule | Impact
Time management | 2 | 1 | 10 | 8 | 6
Payment method not clear | 3 | 1 | 7 | 7 | 7
API is not easily accessible | 9 | 1 | 6 | 9 | 6
Untrained staff | 8 | 1 | 7 | 9 | 9
Privileges Ambiguity | 9 | 1 | 8 | 8 | 9
Stakeholders Ambiguity | 9 | 1 | 10 | 10 | 7