## Slide 1
Critical Path Method (CPM)
Software Project Management

## Slide 2: Critical Path Method (CPM)
Elements: Activities & Events
Feature: Precedence relations
Activity | Duration | Precedence
A | 4 | -
B | 5 | -
C | 3 | A
D | 3 | A
E | 2 | B, C
Activities Table

## Slide 3: Critical Path Method (CPM)
Graphical representation :
Activities :
(edges)
Events :
(vertices)
C
T
(Time reqd. for activity)

## Slide 4: Critical Path Method (CPM)
Precedence:
Activities B & C precede Activity E
C
B
E
This “Event” cannot occur before both activities B & C have been completed

## Slide 5: Critical Path Method Example
Activity | Duration | Precedence
A | 4 | -
B | 5 | -
C | 3 | A
D | 3 | A
E | 2 | B, C

## Slide 6: Critical Path Method (CPM)
The project sequence graph is constructed:
C
B
E
A
D
Now what ???
Project
Start
Project
End

## Slide 7: Critical Path Method (CPM)
Events are consolidated to provide the specified precedence.
C
B
E
A
D
Project
Start
Project
End

## Slide 8: Critical Path Method (CPM)
Activity times (duration) are added next :
C
B
E
A
D
Project
Start
Project
End
5
3
3
2
4

## Slide 9: Critical Path Method (CPM)
The CRITICAL PATH is the path through the project on which any delay will cause the completion of the entire project to be delayed:
C
B
E
A
D
Project
Start
Project
End
5
3
3
2
4

## Slide 10: Critical Path Method (CPM)
For fairly simple projects, the critical path is usually the longest path through the project.
For projects with several parallel and interlinked activities, this may not always be the case.
For more complicated projects, the critical path can be determined with an ‘earliest time’ forward sweep through the diagram followed by a ‘latest time’ reverse sweep.

## Slide 11: PERT/CPM
PERT stands for Program Evaluation and Review Technique.
CPM stands for Critical Path Method.
PERT/CPM is used to plan the scheduling of individual activities that make up a project.
PERT/CPM can be used to determine the earliest/latest start and finish times for each activity, the entire project completion time and the slack time for each activity.

## Slide 12: Importance of PERT/CPM
By using PERT and CPM analysis you will be able to answer questions such as:
When will the entire project be completed?
What are the critical activities or tasks in the project, that is, the ones that will delay the entire project if they are late?
Which are the noncritical activities, that is, the ones that can run late without delaying the whole project’s completion time?
What is the probability that the project will be completed by a specific date?
At any particular date, is the project on schedule, behind schedule, or a head of the schedule?
On any given date, is the money spent equal to, less than, or greater than the budgeted amount?
Are there enough resources available to finish the project on time?
If the project is to be finished in a shorter amount of time, what is the best way to accomplish this at the least cost? (crash analysis)

## Slide 13: CPM
Finding the critical path is a major part of controlling a project.
The activities on the critical path represent tasks that will delay the entire project if they are delayed.
Manager gain flexibility by identifying noncritical activities and replanning, rescheduling, and reallocating resources such as personnel and finances

## Slide 14: Project Network
A project network can be constructed to model the precedence of the activities.
The arcs of the network represent the activities.
The nodes of the network represent the start and the end of the activities.
(Done in start)
A critical path for the network is a path consisting of activities with zero slack. And it is always the longest path in the project network.

## Slide 15: Drawing the project network (AOA)
An activity carries the arrow symbol, . This represent a task or subproject that uses time or resources
A node (an event), denoted by a circle , marks the start and completion of an activity, which contain a number that helps to identify its location. For example activity A can be drawn as:
A
1
2
3 days
This means activity A starts at node 1 and finishes at node 2 and it will takes three days

## Slide 16: Determining the Critical Path
Step 1: Make a forward pass through the network as follows: For each activity i beginning at the Start node, compute:
  Earliest Start Time (ES) = the maximum of the earliest finish times of all activities immediately preceding activity i. (This is 0 for an activity with no predecessors.). This is the earliest time an activity can begin without violation of immediate predecessor requirements.
  Earliest Finish Time (EF) = (Earliest Start Time) + (Time to complete activity i. This represent the earliest time at which an activity can end.
The project completion time is the maximum of the Earliest Finish Times at the Finish node.

## Slide 17: Determining the Critical Path
Step 2: Make a backwards pass through the network as follows: Move sequentially backwards from the Finish node to the Start node. At a given node, j, consider all activities ending at node j. For each of these activities, (i,j), compute:
  Latest Finish Time (LF) = the minimum of the latest start times beginning at node j. (For node N, this is the project completion time.). This is the latest time an activity can end without delaying the entire project.
  Latest Start Time (LS) = (Latest Finish Time) - (Time to complete activity (i,j)). This is the latest time an activity can begin without delaying the entire project.

## Slide 18: Determining the Critical Path
Step 3: Calculate the slack time for each activity by:
Slack = (Latest Start) - (Earliest Start), or
= (Latest Finish) - (Earliest Finish).
A critical path is a path of activities, from the Start node to the Finish node, with 0 slack times.

## Slide 19: Example: ABC Associates
Consider the following project:
Immediate
Activity Predecessor time (days)
A -- 2
B A 15
C A 10
D A 13
E A 18
F C,D 15
G B,F 10
H G,E 5