## Slide 1: Using Earned Value to Monitor Project Performance

## Slide 2: Earned Value Management (EVM)
Earned Value Management (EVM) is a technique that measures project performance against the project baseline.

## Slide 3: Earned Value Management (EVM)
It’s common to think about projects with binary thinking:
Ahead of schedule vs. behind schedule
Over budget vs. under budget
Both project performance factors have a direct impact on the total project cost. What will be the total cost of my project if I'm ahead of schedule but my costs are higher than expected? If I'm behind schedule but my costs are lower? EVM provides great information to help with these questions.

## Slide 4: Planned Value (PV)
Also known as Budgeted Cost of Work Scheduled (BCWS), Planned Value is the amount of the task that is supposed to have been completed, in terms of the task budget. It is calculated from the project budget.
PV = Percent Complete (planned) x Task Budget

## Slide 5: Planned Value (PV)
You have a project to be completed in 12 months and the total cost of the project is 100,000 PKR. Six months have passed and the schedule says that 50% of the work should be completed.
= 50% of BAC = 50% of 100,000 = (50/100)X 100,000 = 50,000
Therefore, the Planned Value (PV) is 50,000 PKR.

## Slide 6: Earned Value (EV)
Also known as Budgeted Cost of Work Performed (BCWP), Earned Value is the amount of the task that is actually completed. It is also calculated from the project budget.
EV = Percent Complete (actual) x Task Budget

## Slide 7: Earned Value (EV)
You have a project to be completed in 12 months and the total cost of the project is 100,000 PKR. Six months have passed and 60,000 PKR has been spent, but on closer review you find that only 40% of the work is completed so far.
Earned Value = 40% of value of total work = 40% of BAC = 40% of 100,000 = 0.4 X 100,000 = 40,000 PKR
Therefore, the Earned Value (EV) is 40,000 PKR.

## Slide 8: Actual Cost (AC)
Also known as Actual Cost of Work Performed (ACWP), Actual Cost is the actual to-date cost of the task.
AC = Actual Cost of the Task

## Slide 9: Actual Cost (AC)
You have a project to be completed in 12 months and the total cost of the project is 100,000 PKR. Six months have passed and 60,000 PKR has been spent, but on closer review you find that only 40% of the work is completed so far. What is the Actual Cost (AC)?
The Actual Cost is 60,000 PKR.

## Slide 10: Schedule Variance (SV)
In this, the first output calculated in the earned value analysis, the project manager obtains a value which tells you the amount that the task is ahead or behind schedule.
SV = EV – PV
If SV is negative, the task is behind schedule.
If SV is zero, the task is on schedule
If SV is positive, the task is ahead of schedule.

## Slide 11: Schedule Performance Index (SPI)
The SPI, similar to the SV, also indicates ahead or behind schedule but gives the project manager a sense of the relative amount of the variance.
SPI = EV/PV
If SPI < 1, the task is behind schedule
If SPI = 1, the task is on schedule
If SPI > 1, the task is ahead of schedule

## Slide 12: Cost Variance (CV)
Similar to the schedule variance, the Cost Variance tells the project manager how far the task is over or under budget.
CV = EV – AC
If CV is negative, the task is over budget
If CV is zero, the project is on budget
If CV is positive, the project is under budget

## Slide 13: Cost Performance Index (CPI)
The CPI, similar to the CV, also indicates over or under budget but gives the project manager a sense of the relative amount of the variance.
CPI = EV/AC
If CPI < 1, the task is over budget
If CPI = 1, the task is on budget
If CPI > 1, the task is under budget

## Slide 14: Budget at Completion (BAC)
This one is easy. It is simply the total project budget, which is the aggregate of all of the task budgets.
BAC = Project Budget

## Slide 15: Estimated at Completion (EAC)
In earned value analysis, the Estimate At Completion, usually abbreviated EAC, is the estimate of the final project cost given the past performance of the project.
Estimate at Completion = (Budget at Completion) / (Cost Performance Index)
EAC = BAC / CPI

## Slide 16: Example
Let’s take a look at an example. Assume we’re halfway through a year-long project that has a total budget of $100,000. The amount budgeted through this six-month mark is $55,000. The actual cost through this six-month mark is $45,000. 50% of the work has been completed.

## Slide 17: Example
Planned Value (PV) = $55,000
Actual Cost (AC) = $45,000
Earned Value (EV) = ($100,000 * 0.5) = $50,000
Schedule Variance (SV) = EV–PV = $50,000-$55,000 = -$5,000 (bad because <0)
Schedule Performance Index (SPI) = EV/PV = $50,000/$55,000 = 0.91 (bad because <1)
Cost Variance (CV) = EV–AC = $50,000-$45,000 = $5,000 (good because >0)
Cost Performance Index (CPI) = EV/AC = $50,000/$45,000 = 1.11 (good because >1)
Estimated at Completion (EAC) = (Total Project Budget)/CPI = $100,000/1.11 = $90,000

## Slide 18: Example
Let’s take a look at an another example. Assume we’re at 4 month mark through a year-long project that has a total budget of $100,000. The amount budgeted through this four-month mark is $30,000. The actual cost through this six-month mark is $32,000. 20% of the work has been completed.