## Slide 1: Introduction to Software Estimation

## Slide 2: Importance
Effective software project estimation is one of the most challenging and important activities in software development.
Proper project planning and control is not possible without a sound and reliable estimate.

## Slide 3: Cont.…
Under-estimating a project leads to under-staffing it (resulting in staff burnout), under-scoping the quality assurance effort (running the risk of low quality deliverables), and setting too short a schedule (resulting in loss of credibility as deadlines are missed).
over-estimating a project can be just about as bad for the organization

## Slide 4: Four basic steps in software project estimation
Estimate the size of the development product. This generally ends up in either Lines of Code (LOC) or Function Points (FP), but there are other possible units of measure.
Estimate the effort in person-months or person-hours.
Estimate the schedule in calendar months.
Estimate the project cost in dollars (or local currency)

## Slide 5: Software Size
Size is a unit of measurement to measure the quantity possessed by an entity.
Example : The volume of the box is measured by calculating its size – the length, breadth, and the height of the box.
There are various units of measures used for describing the size of a software application

## Slide 6: Sizing vs. Estimation
software sizing and effort estimation are not the same.
Sizing is a formal, usually a scientific way of measuring the size of a software application.
Most sizing techniques are algorithmic based, and is consistently understood irrespective of who is performing the activity.

## Slide 7: Cont.…
In case of estimation, it is an activity where a lot of assumptions and rationale play a vital role.
The experience of the person performing the activity impacts the effort estimate.
Sizing is done to count the size of the application; whereas estimation is used to estimate the effort taken to develop the application.

## Slide 8: Cont.…
For example: Consider the case of a person traveling from point A to point B.
  Estimate Distance
    in terms of miles, kilometers, yards, etc.
    Irrespective of who measured it.
    It will always be 2 miles.
  Estimate time required to cover the distance
    Various assumptions and constraints like traffic, mode of transportation, weather information, etc., will also be considered.
    final figure would differ based on the assumptions various people would make.

## Slide 9: Cont…
Similarly, for the case of sizing and effort estimation, sizing is like determining the distance, and estimation is like determining the time.

## Slide 10: Sizing and effort estimation
sizing is usually an algorithmic, structured exercise.
many considerations, assumptions, and risks are involved in the case of effort estimation.
Size forms the base; for deriving the effort estimate, estimated cost, estimated duration, and finally, to draw up the schedule.

## Slide 11: Example scenario
Consider the size of a retail application derived as 1000 function points.
Consider that the current productivity baseline is 5 function points per hour.
The effort required to develop the application
  1000 divided by 5 which equals 200 hours.
Once the effort has been estimated, the cost can be easily determined.

## Slide 12: Cont.…
consider that the average billing rate is 25 dollars per hour and other costs are 300 dollars. Thus, the total estimated cost is 200 multiplied by 25 plus 300 dollars which equals 5300 dollars.
The estimated duration for completion of the application development is also determined based on the number of people assigned, number of working days in a calendar month, and the number of working hours in a day.

## Slide 13: Cont.…
Consider that the number of people assigned is 2, the calendar days in a month is 22 (excluding weekends and holidays), and typical working hours in a day is 8hrs.
Based on these and the estimated effort, the estimated duration would be 0.56 person months or 12 person days.

## Slide 14: Cont.…
The final step in this process would be to develop the schedule.
The schedule consists of the break-up of the tasks required to develop the application along with the resource allocation for each task.
This is done using Work Breakdown Structure (WBS)